## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | NATIONAL CAPITAL REGION |  | CALENDAR YEAR: | 2023
PROVINCE: | CITY OF MALABON |  | QUARTER: | 2
CITY/MUNICIPALITY: | CITY OF MALABON
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Installation of 65 sets Hybrid Solar Streetlights along Sanciangco St. (from P. Aquino Ave. to M.H. Del Pilar St.) | Tonsuya, Niugan and Catmon | 4467971 | [5 empty] | Re-aligned
Rehabilitation of Streetlights | various barangays | 7500000 | [5 empty] | Re-aligned
Installation of Hybrid Solar Streetlights | Various Barangays | 22900000 | [5 empty] | For Procurement
Rehabilitation of various multi-purpose halls | various barangays | 10000000 | [5 empty] | Pipelining
Construction of Hulong Duhat Health Center (Phase II) | Hulong Duhat | 20000000 | [5 empty] | Re-aligned
Construction of Hulong Duhat Health Center (Phase II) | Hulong Duhat | 30000000 | [5 empty] | Pipelining
Rehabilitation of various facilities at Ospital ng Malabon | Tañong | 5000000 | [5 empty] | Pipelining
ECONOMIC DEVELOPMENT
Upgrading/Rehabilitation of Alupihang Dagat St. (portion), including drainage | Longos | 6000000 | [5 empty] | For Procurement
Upgrading/Rehabilitation of Tila St., including drainage | Maysilo | 6000000 | [5 empty] | Pipelining
Upgrading/Rehabilitation of various alley along Katarungan St., including drainage | Muzon | 3000000 | [5 empty] | For Procurement
Upgrading/Rehabilitation of various alley along Kaunlaran St., including drainage (Phase III) | Muzon | 4800000 | [5 empty] | For Procurement
Upgrading/Rehabilitation of Delos Santos St., including drainage | Tonsuya | 8000000 | [5 empty] | For Procurement
Construction of Footbridge along Sucul Creek and Letre Creek | Tonsuya | 4000000 | [5 empty] | For Procurement
Rehabilitation of Ignacio St., including drainage | Tugatog | 8036760 | [5 empty] | Re-aligned
Upgrading/Rehabilitation of Ignacio St., including drainage | Panghulo | 7500000 | [5 empty] | For Procurement
Upgrading/Rehabilitation of various Open Space and alley including drainage | Longos | 10000000 | [5 empty] | Re-aligned
Upgrading/Rehabilitation of Roads and alleys including drainage | Various Barangays | 29898547.6 | [5 empty] | Re-aligned
Upgrading/Rehabilitation of Roads and alleys including drainage | Various Barangays | 30966488.6 | [5 empty] | For Procurement
ENVIRONMENTAL DEVELOPMENT
Upgrading/Rehabilitation of various drainage | various barangays | 6000000 | [5 empty] | Re-aligned
Construction/Modernization of Dulong Adante Pumping Station and Floodgate | Tañong | 17000000 | [5 empty] | Pipelining
Greening and Beautification Program | City-Wide | 57600000 | [5 empty] | Pipelining
Sagip Kapaligiran: Malabon Ahon Tungo sa Malusog at Malinis na Kapaligiran | City-Wide | 22572000 | January 2023 | December 2023 | 38.85% | 8769165 |  | On-going
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
Prepared by: |  |  |  |  | Noted by:
ENP. MA. SHELLA S. CABRERA, MPA | [5 empty] | HON. JEANNIE N. SANDOVAL
OIC - City Budget Department | [5 empty] | City Mayor

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43