## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | NATIONAL CAPITAL REGION |  | CALENDAR YEAR: | 2023
PROVINCE: | CITY OF MALABON |  | QUARTER: | 3
CITY/MUNICIPALITY: | CITY OF MALABON
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT | [8 empty] | 67900000
Installation of Hybrid Solar Streetlights | Various Barangays | 22900000 | [5 empty] | ● As realigned under City Reso. No. 128-2023 dated July 10, 2023 ● For Implementation as per issued NTP
Rehabilitation of various multi-purpose halls | various barangays | 10000000 | [5 empty] | ● For Implementation as per issued NTP
Construction of Hulong Duhat Health Center (Phase II) | Hulong Duhat | 30000000 | [5 empty] | ● As realigned under City Reso. No. 128-2023 dated July 10, 2023 ● Pipelining
Rehabilitation of various facilities at Ospital ng Malabon | Tañong | 5000000 | [5 empty] | ● Pipelining
ECONOMIC DEVELOPMENT
Upgrading/Rehabilitation of Alupihang Dagat St. (portion), including drainage | Longos | 6000000 | [5 empty] | ● For Implementation as per issued NTP | 70266448.6
Upgrading/Rehabilitation of Tila St., including drainage | Maysilo | 6000000 | [5 empty] | ● For Implementation as per issued NTP
Upgrading/Rehabilitation of various alley along Katarungan St., including drainage | Muzon | 3000000 | [5 empty] | ● For Implementation as per issued NTP
Upgrading/Rehabilitation of various alley along Kaunlaran St., including drainage (Phase III) | Muzon | 4800000 | [5 empty] | ● For Implementation as per issued NTP
Upgrading/Rehabilitation of Delos Santos St., including drainage | Tonsuya | 8000000 | [5 empty] | ● For Implementation as per issued NTP
Construction of Footbridge along Sucul Creek and Letre Creek | Tonsuya | 4000000 | [5 empty] | ● Bid Out
Upgrading/Rehabilitation of Ignacio St., including drainage | Panghulo | 7500000 | [5 empty] | ● For Implementation as per issued NTP
Upgrading/Rehabilitation of Roads and alleys including drainage | Various Barangays | 30966448.6 | [5 empty] | ● As realigned under City Reso. No. 128-2023 dated July 10, 2023 ● For Implementation as per NTP issued
ENVIRONMENTAL MANAGEMENT
Construction/Modernization of Dulong Adante Pumping Station and Floodgate | Tañong | 17000000 | [5 empty] | ● Bid Out | 91172000
Greening and Beautification Program | City-Wide | 51600000 | [5 empty] | ● Pipelining
Sagip Kapaligiran: Malabon Ahon Tungo sa Malusog at Malinis na Kapaligiran | City-Wide | 22572000 | January 2023 | December 2023 | 42.94% | 9691425 |  | ● On-going
229338448.6
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
ENP. MA. SHELLA S. CABRERA, MPA | [5 empty] | HON. JEANNIE N. SANDOVAL
OIC - City Budget Department | [5 empty] | City Mayor

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43