## Form 6a -TFU (3)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: | NATIONAL CAPITAL REGION |  | CALENDAR YEAR: | 2023
PROVINCE: | CITY OF MALABON |  | QUARTER: | 3
CITY/MUNICIPALITY: | CITY OF MALABON
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 | February 14, 2018 | 2022-12-01 | 97.02% | 4706030 |  | Remaining fund balance is P144,492.89, yet to be utilized by BFP-Malabon
Implementation of Medical Assistance to Indigent & Poor patients in Government hospitals | Ospital ng Malabon | 44850000 | January 2021 | December 2024 | 59.71% | 26778351.97 |  | Ongoing project with available fund balance of P18,071,648.13 (Note :MOA will continue to be valid and binding until terminated by any party or automatically terminated secondary to exhaustion or utilization of tansferred fund)
Financial assistance to health sector (OSMAL) development project to assist the government hospital in providing medical services and support to paupers and prioritize the needs of the underpriveleged, sick ,elderly, disabled as per approved Memorandum dated March 31, 2022. | Ospital ng Malabon | 50000000 | June 20, 2022 | June 2024 | 43.4% | 21701291.58 | 1 | Ongoing project with available fund balance of P28,298,708.42 (from June 2023 extended to June 2024)
Fund transfer from DOH as support to the city's operations as Universal Health Care ( UHC) Integration site for efficient and effective implementation of planned activities. | City Health Department | 1000000 | 2023-09-01 | December 2023 |  |  |  | on going project
fund transferred from DOH-MMCHD for Health Emeragency Allowance (HEA) for February -June 2022 | Various health facilities | 10328250 | [5 empty] | for payout
Fund transfer for the construction of Hulong Duhat Super Health | Hulong Duhat Super Health Center | 11700000 | [5 empty] | Procurement stage @ BAC Office
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
MA. SHELLA S. CABRERA |  |  | ANA D. JUANITO |  |  | HON. JEANNIE N. SANDOVAL
OIC- City Budget Department |  |  | OIC - City Accountant |  |  | City Mayor

## Form 6b - TFU (hidden)
LOCAL GOVERNMENT SUPPORT FUND (Report on Fund Utilization and Status of Program/Project Implementation)
REGION: |  |  | CALENDAR YEAR:
PROVINCE: |  |  | QUARTER:
CITY/MUNICIPALITY: |  |  | OFFICE:
Amount
Fund Source | Date of Notice of Authority to Debit Account Issued | Type of Program/Project | Name Title of Program/Project | Specific Location | Mechanism/Mode of Implementation | Estimated Number of Beneficiaries | Received | Obligation | Disbursement | Estimated Completion (Month and Year) | Remarks on Program/Project Status
Certified Correct by: |  |  |  |  | Attested by:
The Local Finance Committee:
Local Chief Executive
City Budget Officer
City Treasurer
City Planning and Development Coordinator
Instructions:
1 | The report shall prepared by the LFC, in coordination with the other local officials concerned (local accountant on the allotment, obligation and disbursements;
local engineers in the status of infrastructure projects, as may be applicable.
2 | The fund source shall be based on the NADAI issued to the cities.
3 | The type of program/project shall be identified, consistent with the projects that may be implemented under the Circular.
4 | Amount received refers to the amount received by the city as its location. It is the amount the NADAI. Obligation refers to the total amount obligated by the
city as of reporting period. Disbursement refers to the total amount paid as of reporting period.
5 | The status of programs/projects refers to the percentage of physical completion or delivery of service as of reporting period.

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2