## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | NATIONAL CAPITAL REGION |  | CALENDAR YEAR: | 2023
PROVINCE: | CITY OF MALABON |  | QUARTER: | 4
CITY/MUNICIPALITY: | CITY OF MALABON
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT | [8 empty] | 15531800.88
Installation of Hybrid Solar Streetlights | Various Barangays | 22900000 | [5 empty] | ● Realigned under City Reso. No. 128-2023 dated July 10, 2023 ● Partialy Completed
▪ Installation of 65 sets Hybrid Solar Streetlights along Sanciangco St. (from P. Aquino Ave. to M.H. Del Pilar St.) Brgys. Tonsuya , Niugan and Catmon |  |  | Sept. 29, 2023 | Nov. 12, 2023 | 100% | 6146749.23
Rehabilitation of various multi-purpose halls | various barangays | 10000000 | Sept. 22, 2023 | Dec. 27, 2023 | 100% | 9385051.65 |  | ● On-going ● 35.09% Utilized
Construction of Hulong Duhat Health Center (Phase II) | Hulong Duhat | 30000000 | [5 empty] | ● As realigned under City Reso. No. 128-2023 dated July 10, 2023 ● Pipelining
Rehabilitation of various facilities at Ospital ng Malabon | Tañong | 5000000 | [5 empty] | ● Pipelining
ECONOMIC DEVELOPMENT | [8 empty] | 61000121.1
Upgrading/Rehabilitation of Alupihang Dagat St. (portion), including drainage | Longos | 6000000 | Sept. 29, 2023 | Dec. 27, 2023 | 100% | 5375817.06 |  | ● Completed
Upgrading/Rehabilitation of Tila St., including drainage | Maysilo | 6000000 | Sept. 26, 2023 | Feb. 22, 2024 | 100% | 8374532 |  | ● Completed
Upgrading/Rehabilitation of various alley along Katarungan St., including drainage | Muzon | 3000000 | 2023-07-03 | 2023-10-07 | 100% | 2955273 |  | ● Completed ● 100% Utilized
Upgrading/Rehabilitation of various alley along Kaunlaran St., including drainage (Phase III) | Muzon | 4800000 | 2023-06-30 | 2023-11-03 | 100% | 4758203 |  | ● Completed ● 100% Utilized
Upgrading/Rehabilitation of Delos Santos St., including drainage | Tonsuya | 8000000 | Sept. 26, 2023 | Jan. 23, 2024 | 100% | 7115786 |  | ● Completed
Construction of Footbridge along Sucul Creek and Letre Creek | Tonsuya | 4000000 | Sept. 29, 2023 | Dec. 27, 2023 | 100% | 2598705.04 |  | ● Completed
Upgrading/Rehabilitation of Ignacio St., including drainage | Panghulo | 7500000 | 2023-07-04 | 2023-11-22 | 100% | 8030693 |  | ● Completed ● 30.49% Utilized
Upgrading/Rehabilitation of Roads and alleys including drainage | Various Barangays | 30966448.6 | [5 empty] | ● Realigned under City Reso. No. 128-2023 dated July 10, 2023 ● Partialy Completed
▪ Upgrading/rehabilitation of Labahita St., including drainage, Brgy. Longos |  |  | Sept. 29, 2023 | Jan. 26, 2024 | 100% | 6039915
▪ Upgrading/rehabilitation of Hasa-Hasa St., including drainage, Brgy. Longos |  |  | Sept. 22, 2023 | 2024-04-25 | 30% | 15751197
ENVIRONMENTAL MANAGEMENT | [8 empty] | 31739253
Construction/Modernization of Dulong Adante Pumping Station and Floodgate | Tañong | 17000000 | Sept. 30, 2023 | Feb. 26, 2024 | 20% | 16627238 |  | ● On-going
Greening and Beautification Program | City-Wide | 51600000 | July 2023 | Dec. 2023 | 2.317% | 1195750 |  | ● On-going
Sagip Kapaligiran: Malabon Ahon Tungo sa Malusog at Malinis na Kapaligiran | City-Wide | 22572000 | January 2023 | December 2023 | 61.65% | 13916265 |  | ● On-going
108271174.98
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document. | [8 empty] | 89045231.94
ENP. MA. SHELLA S. CABRERA, MPA | [5 empty] | HON. JEANNIE N. SANDOVAL
OIC - City Budget Department | [5 empty] | City Mayor

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43