## Form 6a -TFU
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: | NATIONAL CAPITAL REGION |  | CALENDAR YEAR: | 2023
PROVINCE: | CITY OF MALABON |  | QUARTER: | 4
CITY/MUNICIPALITY: | CITY OF MALABON
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 | February 14, 2018 | 2022-12-01 | 97.02% | 4706030 |  | Remaining fund balance is P144,492.89, yet to be utilized by BFP-Malabon
DOH-Implementation of Medical Assistance to Indigent & Poor patients in Government hospitals | Ospital ng Malabon | 44850000 | January 2021 | December 2024 | 71.55% | 32090479.37 |  | Ongoing project with available fund balance of P12,759,520.63 (Note :MOA will continue to be valid and binding until terminated by any party or automatically terminated secondary to exhaustion or utilization of tansferred fund)
President Soci Civic Project Fund -Financial assistance to health sector (OSMAL) development project to assist the government hospital in providing medical services and support to paupers and prioritize the needs of the underpriveleged, sick ,elderly, disabled as per approved Memorandum dated March 31, 2022. | Ospital ng Malabon | 50000000 | June 20, 2022 | June 2024 | 43.4% | 21701291.58 | 1 | Ongoing project with available fund balance of P28,298,708.42 (from June 2023 extended to June 2024)
Fund transfer from DOH as support to the city's operations as Universal Health Care ( UHC) Integration site for efficient and effective implementation of planned activities. | City Health Department | 1000000 | 2023-09-01 | March 2024 |  |  |  | on going project
Fund fund transferred from DOH-MMCHD for Health Emeragency Allowance (HEA) for February -June 2022 | Various health facilities | 10328250 | 2023-11-08 | 2023-11-13 | 99.83% | 10310250 |  | Paid HEA under ROD # 300-ecs-2023-01-001 dated 11/13/2023. The unused amount of P18,000.00 was returned to DOH under check no. 371321 dated 12/04/2023, DOH O.R. # 5712099 dated 12/11/2023.
Fund transfer for the construction of Hulong Duhat Super Health Center | Hulong Duhat Super Health Center | 11700000 | 2023-11-10 | 2024-05-14 |  |  |  | For first partial billing (20.94%)
Fund transferred from DOST for the project titles " Improving the Production Capability of JUPCMO and Support to the Reformation Program in Bahay Sandigan and Bahay Pag-asa | Barangay Catmon and Bahay Sandigan and Bahay Pag-asa | 1047270 | 2022-10-01 | 2023-10-01 |  |  |  | Breakdown of the amount transferred, date started and target date of completion: P 487,400.00- 11/2022 -10/2023 559,870.00- 10/2022 - 10/2023 On going project
Department of Tourism-Fund transferred for Local Tourism Development Plan Funding Assistance to the City of Malabon | City Tourism Office | 2000000 | [5 empty] | for implementation
DOH -Fund transfer to the grant of Heath Emergency Allowance to Public and Non Heath Care Workers in the facilities involved in COVID 19 Response. | Ospital ng Malabon | 5248250 | [5 empty] | Fund transfer was recorded by CAD last December 19, 2023.
DOH -Fund transfer to the grant of Heath Emergency Allowance to Public and Non Heath Care Workers in the facilities involved in COVID 19 Response. | Catmon Health Center,MNHS 2, MNHS isolation facility and Oreta Sports Complex | 1254000 | [5 empty] | Fund transfer was recorded by CAD last December 28, 2023.
DOH -Fund transfer to the grant of Heath Emergency Allowance to Public and Non Heath Care Workers in the facilities involved in COVID 19 Response. | Various health facilities involved in COVID 19 Response | 18504000 | [5 empty] | Fund transfer was recorded by CAD last December 28, 2023.
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
MA. SHELLA S. CABRERA |  |  | ATTY. ANA D. JUANITO, CPA |  |  | HON. JEANNIE N. SANDOVAL
OIC- City Budget Department |  |  | OIC - City Accountant |  |  | City Mayor
Note:
Subject for Adjustment

## Form 6b - TFU (hidden)
LOCAL GOVERNMENT SUPPORT FUND (Report on Fund Utilization and Status of Program/Project Implementation)
REGION: |  |  | CALENDAR YEAR:
PROVINCE: |  |  | QUARTER:
CITY/MUNICIPALITY: |  |  | OFFICE:
Amount
Fund Source | Date of Notice of Authority to Debit Account Issued | Type of Program/Project | Name Title of Program/Project | Specific Location | Mechanism/Mode of Implementation | Estimated Number of Beneficiaries | Received | Obligation | Disbursement | Estimated Completion (Month and Year) | Remarks on Program/Project Status
Certified Correct by: |  |  |  |  | Attested by:
The Local Finance Committee:
Local Chief Executive
City Budget Officer
City Treasurer
City Planning and Development Coordinator
Instructions:
1 | The report shall prepared by the LFC, in coordination with the other local officials concerned (local accountant on the allotment, obligation and disbursements;
local engineers in the status of infrastructure projects, as may be applicable.
2 | The fund source shall be based on the NADAI issued to the cities.
3 | The type of program/project shall be identified, consistent with the projects that may be implemented under the Circular.
4 | Amount received refers to the amount received by the city as its location. It is the amount the NADAI. Obligation refers to the total amount obligated by the
city as of reporting period. Disbursement refers to the total amount paid as of reporting period.
5 | The status of programs/projects refers to the percentage of physical completion or delivery of service as of reporting period.

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
38