## 4th qtr 2025
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: | NATIONAL CAPITAL REGION |  | CALENDAR YEAR: | 2025
PROVINCE: | CITY OF MALABON |  | QUARTER: | 4
CITY/MUNICIPALITY: | CITY OF MALABON
b
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Improvement and maintenance of the Malabon City Bureau of Fire Protection Stations | Malabon City Fire Station-# 70 Gov. Pascual Ave. Potrero, Malabon City | 4850522.89 | February 14, 2018 |  | 100% | 4850320 |  | Remaining fund balance is P 202.89
DOH-Implementation of Medical Assistance to Indigent & Poor patients in Government hospitals | Ospital ng Malabon | 111150000 | 2021-01-01 | December 2025 | 66.53% | 73950207.63 |  | Ongoing project with available fund balance of P 37,199,792.37
Department of Agriculture-Financial Assistance for the implementation of "Enhanced Kadiwa ni Ani at Kita Financial Grant Assistance Program" | Nuestra Señora Del Rosario Credit Cooperative and Ang Palengke natin Multi Purpose Cooperative | 2000000 | January 26, 2022 | May 31,.2022 | 45.82% | 916377.2 |  | Remaining fund balance is P 1,083,622.80
President Socio Civic Project Fund -Financial assistance to health sector (OSMAL) development project to assist the government hospital in providing medical services and support to paupers and prioritize the needs of the underpriveleged, sick ,elderly, disabled person. | Ospital ng Malabon | 50000000 | June 20, 2022 | June 2025 | 92.74% | 46372123.76 | 2 | Available fund balance of P 3,627,876.24 was returned to the Office of the President under check no. 371454 dated 11/14/2025 | returned unused amt.
Fund transfer from DOH as support to the city's operations as Universal Health Care ( UHC) Integration site for efficient and effective implementation of planned activities. | City Health Department | 1000000 | 2023-09-01 | December 2024 | 94.19% | 941937.23 |  | Available fund balance of P 58,062.77 was returned to DOH under check no. 371455 dated 12/10/2025 | to return unused amount , w prepared DV
Fund transferred from DOST for the project titles " Improving the Production Capability of JUPCMO and Support to the Reformation Program in Bahay Sandigan and Bahay Pag-asa | Barangay Catmon and Bahay Sandigan and Bahay Pag-asa | 1047270 | 2022-10-01 | 2023-10-01 | 93.8% | 982315 | 1 | with fund balance amounting to P 64,955.00
Bureau of Fire-Procurement of supplies and equipment for use of the city BFP Fire Station | Malabon City Fire Station-F.Sevilla Blvd. cor Sacristia St.San Agustin, Malabon City | 13148944.6 | January 19, 2024 |  |  |  |  | with issued CAF no. 300-2401-006 dated 01/19/2024. Items are yet to be delivered by the supplier.
BOT- implementation of priority programs of various local gov't units (LGUs) chargeable against the Local Gov't Support Fund-Financial Assistance for other ICTS and Infra Development-Human Resource Management System (HRMS) | City Gov't. of Malabn | 20000000 | June 4, 2024 | 2025-12-31 | 70% | 13999999 |  | Partial Payment for the Procurement of Human Resource Information System (HRIS) with Hardware and Software Components | partial payment for the implementation of the project
FY 2023 Seal of Good Local Governance Incentive Fund (SGLG) for procurement of One (1) Service Vehicle | City Gov't. of Malabn | 2300000 | July 15, 2024 |  |  |  |  | with issued CAF # 300-2407-051 dated 07/15/2024
Fixed Tranche 2024 from DOH-MMCHD | City Health Department | 1000000 | September 16, 2024 | July 2025 | 93.87% | 938651 |  | Available fund balance of P 61,349.00 was returned to DOH under check no. 371456 dated 12/10/2025 | with FUR still for signature, to prepare DV for return
Expansion of Active Transport Infrastructure in Malabon City | Malabon City | 7062900.29 | [5 empty] | Transferred per LDDAP-ADA No. 102101-10-038-2024, dated 10/8/2024 under LBP account no 0652-1037-58 at LBP Malabon Branch
FY 2024 Seal of Good Local Governance Incentive Fund (SGLG)-Procurement of IT equipment. | Malabon City | 2000000 | October 16,2025 |  |  |  |  | with issued CAF # 300-2410-011 dated 10/16/2025
Bureau of Fire-Procurement of 1000L Mini Penetrator Fighting Truck | Malabon City Fire Station-F.Sevilla Blvd. cor. Sacristia St. San Agustin, Malabon City | 6679380.91 | September 25, 2025 |  |  |  |  | with issued CAF # 300-2509-010 dated 9/25/2025
Fixed Tranche 2025 from DOH-MMCHD | City Health Department | 1000000 | [5 empty] | Recorded by CAD under JEV # 300-12-077 dated 12/19/2025
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ENP MARLYN S. LAZARO, MMEP |  | ATTY. ANA D. JUANITO, CPA |  |  |  | HON. JEANNIE N. SANDOVAL
City Budget Officer |  | OIC - City Accountant |  |  |  | City Mayor